## Actions (hidden)
ACTION TRACKER
Date | Num | Action | Who? | Due Date | Status | Update/Comments
18/09/2012 | 1899-12-31 | Submit an updated commercial offer to include the costs of: additional software licenses, HW, integration points, training and maintenance | AVAYA/METCO | 30/09/2012 | Closed
2012-03-10 | 1900-01-01 | Conference call to discuss and agree on number of functionalities and integration points | AVAYA/METCO | 2012-04-10 | Closed
2012-03-10 | 1900-01-02 | Send Letter of Intent (LOI) to METCO/AVAYA to ensure maintaining the mobilisation date (15/10/2012) | Wataniya | 2012-04-10 | Closed
2012-03-10 | 1900-01-03 | Clarify about the number of integration functions mentioned in the proposal and map them against the workstreams | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-04 | Quote for 2 DB servers instead of 1 | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-05 | Quote for Oracle licenses | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-06 | Revise servers memory and quote for 16 GB memory instead of 4 GB | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-07 | Update the network diagram to include 2 sessions manager as per the BOQ submitted earlier | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-08 | Quote for Disaster Recovery separately | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-09 | Development Environment to be listed and quoted | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-10 | Quote for 30 ports instead of 10 ports | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-11 | Add the existing Wataniya boxes into the submitted design network diagram | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-12 | Submit the revised commercial | AVAYA/METCO | 2012-07-10 | Closed
2012-03-10 | 1900-01-13 | Review project plan (timelines, dependencies, missing milestones like testing, etc) | Wataniya | 2012-08-10 | Closed
2012-03-10 | 1900-01-14 | Review commercials | Wataniya | 2012-08-10 | Closed
2012-03-10 | 1900-01-15 | Identify TPMO resource for the IVR Project | Wataniya | 2012-09-10 | Closed
2012-03-10 | 1900-01-16 | Define Phase 0 Scope | Wataniya | 2012-09-10 | Closed
2013-04-02 | 1900-01-17 | AVAYA to confirm on the date of the workshop to discuss and finalize the remaining call flows and the integration part | AVAYA/METCO | 2013-04-02 | Closed
2013-04-02 | 1900-01-18 | Map WT floated requirements with the requirement documented by AVAYA to ensure that all requirements are discussed and included in the solution which will be delivered by AVAYA. | AVAYA/METCO | 2013-05-02 | Closed
2013-04-02 | 1900-01-19 | Map WT floated requirements and scope it into phases (i.e. ph1 IVR, ph2 CF, etc) | AVAYA/METCO | 2013-05-02 | Closed
2013-04-02 | 1900-01-20 | Provide a comparison sheet between Call back request and Call back assist as agreed | AVAYA/METCO | 2013-05-02 | Closed
2013-04-02 | 1900-01-21 | AVAYA to draft details and call flows based on the information gathering during the workshop | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-22 | Provide the updated “rack layouts” ,“power consumption“ and “required interfaces per server” | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-23 | Provide the updated “agreed on” architectural infrastructure document | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-24 | Provide the updated data flow diagram, showing the call routing since generation on a customer mobile till termination either in AAEP or AACC. Avaya will present that in a diagram format along with scenarios and examples showing the call routing details | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-25 | Provide feedback on the possibility of breaking the existing PABX clustering and perform the following procedure: break existing PABX clustering àshift core0 to SBAà re-configure core0 in SBA, but still serve the customers in Wataniya tower via core1 àGO-LIVE on SBA core0 àshift core1 to SBA. If that is doable, then we will apply that plan. If not, than we have to rely on METCO providing temporary similar PABX during main PABX shift to SBA | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-26 | Provide feedback on the CRM integration as discussed during the workshop | AVAYA/METCO | 2013-07-02 | Closed
2013-04-02 | 1900-01-27 | Provide feedback on the 2nd chance functionality | AVAYA/METCO | 21/02/2013 | Closed
2013-04-02 | 1900-01-28 | Provide solution to call back assist and virtual hold requirement | AVAYA/METCO | 18/02/2013 | Closed | Not Feasible as confirmed by AVAYA/METCO
14/02/2013 | 1900-01-29 | Provide the final HLD document for Wataniya review | AVAYA/METCO | 20/03/2013 | Closed | New due date is 20/03/2013
14/02/2013 | 1900-01-30 | Start drafting the LLD document and collect all the required information from Wataniya | AVAYA/METCO | 25/02/2013 | Closed
18/02/2013 | 1900-01-31 | Provide the updated project plan based on the new timelines | AVAYA/METCO | 21/02/2013 | Closed
18/02/2013 | 1900-02-01 | Tech Planning team to decide on the CC payment gateway approach | Wataniya | 28/02/2013 | Closed
18/02/2013 | 1900-02-02 | Tech Planning team to agree on the required web services to avoid delay in integration timelines | Wataniya | 28/02/2013 | Closed

## Decisions (hidden)
DECISION TRACKER
Date | Num | Decisions | Who made it? | Decision Date | Status | Update/Comments
2012-09-02 | 1 | AVAYA was selected as "Single vendor source" for the IVR project | Scott Gegenheimer | 2012-09-02 | Complete | Michael Cooper presented in the CxO's meeting and decision was made on the spot.
| 2 | The single source decision was halted | Abdulaziz Fakhrou / CxO's |  | Complete | Concern on governance
21/06/2012 | 1900-01-02 | Decision was changed to go for RFQ to AVAYA, GENESIS & CISCO instead of single source | Abdulaziz Fakhrou / CxO's | 21/6/2012 | Complete | Private meeting
24/07/2012 | 1900-01-03 | Decision was changed again to select AVAYA as "single vendor source" for the IVR project | CxO's | 24/07/2012 | Complete | Single Source as AVAYA is mentioned in the 2nd version of ED - signed off on 15/08/2012

## Action Log
Action Log
Sequence | Tested By | Date | Campaign | Number | Last Menu | Final action

## Issue Log
Issues Log | [8 empty] | `
Log ID | Reported Date | Reported by | Phone Number | Test ID | Campaign | Description | Issue Type | Status | Resolution | Resolved Date

## Data
Campaigns | Type | Status
Loyalty | Functionality | Open
Telemarketing | Announcement | Closed
Collection |  | Resolved